## Group Details
Course | PMC-444- ZAA
Group Number | 3
Names | Student Email
Yuvraj Singh | Yuvraj-singh5@myseneca.ca
Mahdi Zangeneh | mzangeneh2@myseneca.ca
Gulshanpreet Singh | gulshanpreet-singh@myseneca.ca
Supreety Datta | sdatta23@myseneca.ca
Aryan Kolath Sumeer | akolath-sumeer@myseneca.ca
Harry Sanil | hsanil@myseneca.ca

## Risk Identification Matrix
Risk ID | Risk Name | Description | Risk Owner | Likelihood | Impact | Mitigation Strategy | Team Member
RI_001 | Technology Adoption | Resistance to new AR/VR technology by employees | HR Manager | High | High | Provide training and awareness sessions | Supreety Datta
RI_002 | Hardware Compatibility | AR/VR hardware may not be compatible with existing systems | IT Manager | Medium | Medium | Ensure hardware/software compatibility before purchase | Mahdi Zangeneh
RI_003 | Budget Overrun | Project expenses exceeding the allocated budget | Finance Manager | Low | Low | Monitor project budget and expenses regularly | Aryan Kolath Sumeer
RI_004 | Software Bugs | Potential bugs in the AR/VR software affecting training | Quality Assurance | Medium | High | Implement robust testing procedures | Yuvraj Singh
RI_005 | Supplier Delays | Delays in AR/VR hardware delivery from suppliers | Procurement Manager | High | Medium | Establish strong supplier relationships and backup suppliers | Gulshanpreet Singh
RI_006 | Lack of Stakeholder Buy-in | Resistance from key stakeholders to adopt Connect Law | Project Manager | High | High | Stakeholder management and regular updates | Supreety Datta
RI_007 | Communication Issues | Inadequate communication channels or tools | Communication Lead | Medium | High | Clear communication plan and effective channels | Yuvraj Singh
RI_008 | Security Breach | Unauthorized access to sensitive information | IT Security Officer | Low | Medium | Regular security audits and access controls | Harry Sanil
RI_009 | Integration Challenges | Difficulty integrating ConnectLaw with existing systems | Integration Specialist | High | High | Effective integration planning and testing | Mahdi Zangeneh
RI_010 | Data Loss or Corruption | Loss or corruption of data during migration | Data Management Team | Medium | High | Data backup and recovery procedures | Aryan Kolath Sumeer
RI_011 | Inadequate Training | Employees not fully trained to use ConnectLaw | Training Coordinator | Low | Medium | Comprehensive training program for employees | Supreety Datta
RI_012 | Scope Creep | Continuous expansion of project scope | Project Manager | High | High | Regular scope review meetings with stakeholders | Gulshanpreet Singh
RI_013 | Lack of User Adoption | Employees not embracing ConnectLaw as the primary tool | Change Management Team | Medium | Medium | Change management and user engagement strategies | Yuvraj Singh

## Qualitative Risk Analysis
Risk ID | Risk Decription | Impact | Probability | Risk Level | Mitigation Strategies
QLR_001 | Some employees may resist due to a lack of familiarity with AR/VR technologies or concerns regarding their use | High | Medium | High | User Training sessions - Employee engagement program
QLR_002 | AR/VR equipment may face technical bugs, compatibility issues, or require frequent updates. | Medium | High | Medium | Through testing - Regular updates
QLR_003 | Budget limit may cause issues | Medium | Medium | Medium | Cost monitoring - Safety Planing
QLR_004 | Limited availability of AR/VR hardware and software in the market. | High | Low | Medium | Merket research - Identify multiple suplliers
QLR_005 | Inadequate user support and training leading to low acceptance rates. | High | Medium | Medium | Comperhensive Training - User support desk
QLR_006 | Technical incompatibility between AR/VR hardware and existing systems. | High | Low | High | Compability Testing - Techniqal expert consultation
QLR_007 | Delays in the delivery of AR/VR equipment due to unforeseen logistical challenges | Medium | Low | Low | Asses Vendor - Comerhensive plan
QLR_008 | Inadequate training material customization for different departments | Medium | Medium | Medium | Department Consultation - Establish Feedback loop
QLR_009 | Limited availability of skilled AR/vR developers | High | Low | Medium | Early recurement - Partnership with local developers
QLR_010 | legal or regulatory changes impacting AR/VR training requirements | High | Low | Medium | Legal Consulation - Flexible training
QLR_011 | Inaccurate data collection methods during training | Medium | Low | Medium | Control checks - training for evaluators
QLR_012 | Limited stakeholder engagement and support | High | Low | High | Stakeholders engagement and communication plan
QLR_013 | Loss of key project team members due to unforeseen circumstances | Medium | Low | Medium | Succession planing - enhance job satisfication
QLR_014 | changes in technology standards affecting the AR/VR equipment | High | Low | Medium | Continious technology monitoring - felxible technology adoption
QLR_015 | Inadequate time for completing AR/VR training modules because of unforeseen conditions | Medium | Medium | High | Detailed project schedule - progress monitoring

## Impact vs. Likelihood graph
Risk ID | Risk Name | Impact on AR/VR Project | Likelihood | Mitigation Strategies
R001 | Security Breach | Potential exposure of confidential AR/VR training content | Medium | Implement SSL, secure authentication, penetration testing
R002 | Lack of Stakeholder Buy-in | Resource constraints impacting AR/VR module deployment | Medium | Showcase benefits with data, secure early endorsements
R003 | Data Loss or Corruption | Setbacks in AR/VR module development due to data issues | Low | Real-time backup systems, data integrity checks
R004 | Scope Creep | Overextension and quality compromise in AR/VR content | Low | Enforce change control, regularly review project scope
R005 | Communication Issues | Misalignment on AR/VR requirements, delays in development | High | Establish communication plan, regular updates
R006 | Integration Challenges | Technical hurdles in AR/VR module functionality | Medium | Integration testing, modular content delivery
R007 | Inadequate Training | Suboptimal utilization of AR/VR training modules | Medium | Detailed training programs, hands-on AR/VR sessions
R008 | Lack of User Adoption | Underutilization of AR/VR modules, poor ROI | Medium | Change management plan, user feedback, gamification

## Quantitative Risk Analysis
Risk ID | Risk Description | Impact | Probability | Risk Level | Mitigation Strategies | Risk Owner | Group Member | Quantified Impact | Quantified Probability of Occurance
QNR_001 | Some employees may resist due to lack of familiarity with AR/VR technologies or concerns regarding their use | 4 | 3 | 12 | User Training sessions - Employee engagement program | Training Manager | Yuvraj Singh | 3 | 2
QNR_002 | AR/VR equipment may face technical bugs, compatibility issues, or require frequent updates | 3 | 4 | 12 | Through testing - Regular updates | IT Support | Mahdi Zangeneh | 2 | 3
QNR_003 | Budget limit may cause issues | 3 | 3 | 9 | Cost monitoring - Safety Planning | Finance Officer | Aryan Kolath Sumeer | 3 | 2
QNR_004 | Limited availability of AR/VR hardware and software in the market | 4 | 1 | 4 | Market research - Identify multiple suppliers | Procurement Officer | Gulshanpreet Singh | 2 | 2
QNR_005 | Inadequate user support and training leading to low acceptance rates | 4 | 3 | 12 | Comprehensive Training - User support desk | HR Manager | Supreety Datta | 3 | 1
QNR_006 | Technical incompatibility between AR/VR hardware and existing systems | 4 | 1 | 4 | Compatibility Testing - Technical expert consultation | Technical Lead | Harry Sanil | 2 | 2
QNR_007 | Delays in the delivery of AR/VR equipment due to unforeseen logistical challenges | 3 | 1 | 3 | Assess Vendor - Comprehensive plan | Logistics Manager | Yuvraj Singh | 3 | 1
QNR_008 | Inadequate training material customization for different departments | 3 | 3 | 9 | Department Consultation - Establish Feedback loop | Training Specialist | Yuvraj Singh | 2 | 2
QNR_009 | Limited availability of skilled AR/VR developers | 4 | 1 | 4 | Early recruitment - Partnership with local developers | HR Manager | Supreety Datta | 3 | 2
QNR_010 | Legal or regulatory changes impacting AR/VR training requirements | 4 | 1 | 4 | Legal Consultation - Flexible training | Compliance Officer | Supreety Datta | 2 | 3
QNR_011 | Inaccurate data collection methods during training | 3 | 1 | 3 | Control checks - training for evaluators | Data Analyst | Aryan Kolath Sumeer | 3 | 2
QNR_012 | Limited stakeholder engagement and support | 4 | 1 | 4 | Stakeholders engagement and communication plan | Project Sponsor | Supreety Datta | 2 | 2
QNR_013 | Loss of key project team members due to unforeseen circumstances | 3 | 1 | 3 | Succession planning - enhance job satisfaction | HR Manager | Supreety Datta | 3 | 1
QNR_014 | Changes in technology standards affecting AR/VR equipment | 4 | 1 | 4 | Continuous technology monitoring - flexible technology adoption | IT Manager | Harry Sanil | 2 | 2
QNR_015 | Inadequate time for completing AR/VR training modules because of unforeseen conditions | 3 | 3 | 9 | Detailed project schedule - progress monitoring | Project Manager | Yuvraj Singh | 3 | 1

## Impact vs.Likelihood(Expensive)
Risk ID | Risk Description | Impact | Likelihood | Risk Priority | Impact Description | Mitigation Strategies | Risk Response | Risk Trigger | Risk Owner
R1 | Budget limit may cause issues | High | Medium | High | May affect project funding and deliverable quality | Secure additional funding sources, revise budgeting | Mitigate | Funding shortfall | Financial Manager
R3 | Limited Availability of Skilled AR/VR Developers | High | Medium | High | May hinder project progress and innovation | Invest in training and external partnerships | Mitigate | New AR/VR tech not adopted | Development Manager
R4 | Inadequate User Support and Training | Medium | Medium | Medium | Could result in low user satisfaction and uptake | Enhance support resources, user-friendly documentation | Mitigate | Support system failure | Support Manager
R5 | Technical Incompatibility with Existing Systems | Medium | Medium | Medium | May cause delays and increase project costs | Regular compatibility checks and system updates | Mitigate | Compatibility update failure | Technical Manager
R6 | Legal or Regulatory Changes | Medium | Medium | Medium | Potential for project delays and legal issues | Stay updated on legal changes, consult legal experts | Transfer | New legal regulation | Legal Advisor
R7 | Limited Stakeholder Engagement and Support | Medium | Medium | Medium | Could reduce project support and increase resistance | Strengthen stakeholder relationships, regular updates | Mitigate | Stakeholder withdrawal | Stakeholder Manager
R8 | Inadequate Time for Completing AR/VR Training Modules | Medium | Low | Medium | May extend project timelines and affect planning | Time management training, buffer time in schedules | Mitigate | Unexpected project delay | Project Coordinator
R9 | Delays in Equipment Delivery | Medium | Medium | Medium | Could delay project deliverables and affect quality | Develop alternative supplier relationships, stockpile key components | Mitigate | Supply chain disruption | Supply Chain Manager
R10 | AR/VR Equipment Technical Issues | Medium | Medium | Medium | May increase maintenance and operational costs | Implement rigorous testing and QA processes | Mitigate | Technical defect discovery | Quality Assurance Manager
R12 | Inaccurate Data Collection Methods | Medium | Low | Medium | May lead to poor decision-making and strategies | Utilize accurate data tracking tools, regular audits | Mitigate | Data discrepancy found | Data Analyst
R2 | Loss of Key Project Team Members | High | Low | Low | Potential project delays due to lack of staff | Staff contingency planning, proactive recruitment | Accept | Key team member leaves | HR Manager
R11 | Limited Availability of AR/VR Hardware and Software | Medium | Low | Low | Could result in inadequate training resources | Invest in robust inventory management systems | Mitigate | Hardware shortage | Inventory Manager
R13 | Changes in Technology Standards | Low | Low | Low | Potential to make project outcomes obsolete | Continuous market research, adopt flexible technologies | Accept | New industry standard | Technology Scout
R14 | Inadequate Training Material Customization | Low | Low | Low | Could lead to ineffective training content | Customize training materials, get user feedback | Mitigate | Negative training feedback | Training Manager
R15 | Employee Resistance to AR/VR Technologies | Low | Low | Low | May result in low employee engagement and retention | Address employee concerns, provide incentives | Mitigate | Employee resistance observed | Change Management Lead

## risk response plans
RISK ID | NAME | DESCRIPTION | RISK OWNER | GROUP MEMBER | RESPONSE STRATEGY | RESPONSE DETAILS
R1 | Budget Limit May Cause Issues | High potential for project funding issues affecting deliverable quality and timelines. | Financial Manager | Yuvraj Singh | Mitigate | Reallocate budget, prioritize critical project activities, apply for additional funding, and maintain a reserve for unforeseen costs.
R3 | Limited Availability of Skilled AR/VR Developers | Challenges in finding and retaining skilled developers might delay project progress. | Development Manager | Gulshanpreet Singh | Avoid | Proactively engage with recruitment agencies to source skilled developers, and establish internship programs with universities.
R2 | Loss of Key Project Team Members | High risk of project delay if key team members leave. | HR Manager | Supreety Datta | Mitigate | Develop a succession plan, increase team engagement, provide competitive benefits, and have a talent retention strategy in place.
R5 | Technical Incompatibility with Existing Systems | Potential delays and costs due to technical incompatibility. | Technical Manager | Harry Sanil | Mitigate | Conduct compatibility testing, plan for system integration, and ensure technical support is available for smooth transition.
R4 | Inadequate User Support and Training | Risk of low user satisfaction and uptake due to inadequate support. | Training Coordinator | Mahdi Zangeneh | Mitigate | Enhance user support resources, develop comprehensive training materials, and implement a user feedback system.
R6 | Legal or Regulatory Changes | Changes in laws may affect project compliance and timelines. | Legal Advisor | Aryan Kolath Sumeer | Transfer | Stay updated on regulatory changes, engage legal expertise to advise on compliance, and adjust project plans accordingly.
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Response Strategy: Mitigate: Conduct regular budget reviews and reallocate funds to prioritize essential project components. Implement cost-saving measures without compromising on critical elements of the AR/VR training modules. Avoid: Seek additional funding sources or increase the budget through reallocation from less critical projects. Transfer: Outsource to cost-effective vendors or partners where possible to spread financial risk. Accept: Have a contingency plan for critical path activities to ensure they can proceed despite financial limitations.
Note on F3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Response Strategy: Mitigate: Develop an in-house training program to upskill current employees. Foster relationships with educational institutions for a steady pipeline of skilled graduates. Avoid: Secure commitments from skilled developers early on in the project timeline to ensure their availability. Transfer: Partner with specialized AR/VR development firms to mitigate the risk of not having skilled developers in-house. Accept: Adjust project milestones to reflect realistic timelines given the available talent pool.
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Response Strategy: Mitigate: Develop comprehensive training manuals and user guides. Provide regular training sessions and workshops for users to familiarize them with the AR/VR technology. Set up a dedicated support desk to address user queries in real-time. Avoid: Conduct a needs assessment before the development of training modules to ensure they are user-friendly and meet the learners' requirements. Incorporate user feedback into the early stages of module development to minimize support needs later on. Transfer: Collaborate with external training providers who specialize in AR/VR to develop and deliver training content. Accept: Recognize that some level of user difficulty is inevitable and plan for ongoing support and iterative improvements to the training modules based on user feedback.